## Slide 1: Class 2DK Group 103 SPRINT 2
Group members:
Maria Inês Alves (1211477)
Alice Resende (1211518)
Henrique Caldas (1211506)
Gonçalo Carneiro (1210809)
Diogo Silva (1211882)

## Slide 2: Sprint planning – Sprint 2
SPRINT BACKLOG | 
Number of stories: 18 | 
Number of bugs: 0 | 
Number of tasks: 9 | 
Number of Management Tasks: 9 | 
Number of team members | Planned: 5 Actual: 5
Total planned estimation vs execution | Planned hours: 90h Executed hours: 4d 16h
Planned Start Date: 4/12/2022 Real Start Date: 4/12/2022
Planned Finished Date: 8/01/2022 Real Finish Date: 4/12/2022

## Slide 3: Sprint planning
Assignment US | Commited? | Todo | Doing | Testing | Done | Blocked
US 110 | Sim |  |  |  | X | 
US 111 | Sim |  |  |  | X | 
US 112 | Sim |  |  |  | X | 
US 104 | Sim |  |  |  | X | 
US 210 | Sim |  |  |  | X | 
US 211 | Sim |  |  |  | X | 
US 213 | Sim |  |  |  | X | 
US 214 | Sim |  |  |  | X | 
US 215 | Sim |  |  |  | X | 
US 216 | Sim |  | X |  |  | 
US 307 | Sim |  |  |  | X | 

## Slide 4: Sprint planning
Assignment US | Commited? | Todo | Doing | Testing | Done | Blocked
US 308 | Sim |  |  |  | X | 
US 309 | Sim |  |  |  | X | 
US 310 | Sim |  |  |  | X | 
US 311 | Sim |  |  |  | X | 
US 406 | Sim |  |  |  | X | 
US 407 | Sim |  |  |  | X | 
US 408 | Sim |  |  |  | X | 
US 409 | Sim |  |  |  | X | 

## Slide 5: Sprint Execution
Issues | Sprint Backlog (a) | Added issues during sprint (b) | Closed issues from initial planning (c) | Closed issues from added ones (d) | Issues not closed (e) | % Execution | 
 |  |  |  |  |  | Planned (c/a) | Total (c+d)/(a+b)
Number of stories (I) | 13 | 5 | 13 | 4 | 1 | 1 | 0,94
Number of bugs (II) | 0 | 0 | - | 0 | - | 0 | 0
Number of tasks (III) | 0 | 7 | - | 7 | - | 0 | 1
TOTAL | 13 | 12 | 13 | 13 | 1 |  | 
Total Estimate | 90h |  |  |  |  |  | 

## Slide 6: Work by team member
Chart: Hours / n. tasks
| Inês (1211477) | Alice (1211518) | Henrique (1211506) | Gonçalo (1210809) | Diogo (1211882)
Horas / tarefas | 8 | 10.75 | 6 | 12 | 9

## Slide 7: Work by type
Chart: Componente
| ESINF | ARQC | BDDAD | …FSIAP
Componente | 0.34 | 0.31 | 0.29 | 0.06

## Slide 8: Sprint Burndown Chart
Print do JIRA após fecho da sprint

## Slide 9: Sprint Review
Date: 05/12/2022
Main conclusions:
Conseguimos definir e redefinir vários sensores de cada tipo e fazer as respetivas leituras diárias para uma ficheiro.
Conseguimos definir as operações agrícolas efetuadas no exploração agrícola e avaliar os dados dos sensores.
Conseguimos definir uma as energias num armazém.
Conseguimos estruturar uma rede de clientes (particulares e empresas) e produtores, para a entrega de cabazes, e definimos o melhor caminho dessa rede.

## Slide 10: Sprint Retrospective
Date: 09/01/2023
What went well?
A componente de física foi realizada sem problemas.
What went wrong?
Durante a ocorrência do Sprint, tivemos outras avaliações nas cadeiras o que não permitiu um bom foco no trabalho.
O enunciado pouco esclarecedor e a descordenação entre professores, tanto quanto ao entendimento do enunciado assim como o que realmente pretendiam.
O enunicado de ESINF e BDDAD era pouco explicito, o que atrasou o projeto.
Má gestão de tempo.
As USs incompletas do sprint 1 tiveram que ser completadas.
What we’ve learned?
Deviamos ter o cuidado de unir as nossas Uss às anterior de forma a fazerem sentido.